## SAMPLING
SLNO | TASK | NO OF DAYS | # PERSON INVOLVED | DEPARTMENTS INVOLVED | PERSON RESPONSIBLE
1 | Yardage (QTY AS PER REQ) | 1 | 1 |  | MERCHNAT
2 | Leg mocks + WASHING | 4 | 3 |  | MERCHANT, TAILOR & WASHING UNIT
3 | Final Selection of Leg mocks | 1 | 2 |  | MD & MERCHANT
4 | Master P.P. Samples | 3 | 4 |  | MD, MERCHANT, TAILOR & WASHING UNIT
5 | Yardage FOR BOOKING SAMPLES
6 | Sample design. | 1 | 2 |  | MD & MERCHANT
7 | Sample making | 7 | 8 |  | MERCHANT,TAILOR, EMB, PRINT, EMBOS, WASHING & FINISHING
8 | FINAL Approval of sample( READY FOR BOOKING) | 1 | 3 |  | MD, SALES TEAM & MERCHANT

## BULK
SLNO | TASK | NO OF DAYS | # PERSONS & DEPARTMENT | PERSON RESPONSIBLE
1 | PO for Bulk Fabric | 1 | 2 | MD & MERCHANT
2 | PO GRN ( AFTER SUPPLIER DISPATCH) | 10 TO 15 | 2 | FABRIC SUPPLIER & MERCHANT
3 | Allocate Fabric to Factory | 1 | 1 | MERCHANT
4 | Factory GRN/ Getting the goods from transport office. | 2 | 1 | MERCHANT
5 | Pattern and Work Order to factory along with P.P Sample. | 3 | 2 | MERCHANT & PATTERN MASTER
6 | Laying Process | 2 | 3 | FACTORY CUTTING SECTION
7 | Marking Process | 1 | 2 | OWN MARKER & FACTORY MARKER
8 | Cutting Process. | 3 | 1 | FACTORY CUTTING SECTION
9 | Sending Stitching trims as per cutting Ratio. | 2 | 2 | MERCHANT & TRIMS SECTION
10 | Printing, embroidery, embossing (As per the design required) | 3 | 2 | MERCHANT & FACTORY PERSONS
11 | LOADING,Stitching & OUT PUT of the garments | 15 |  | FACTORY
12 | WASHING APPROVAL BULK | 2 |  | MERCHANT & WASHING UNIT
13 | Washing of the garments | 7 |  | MERCHANT & WASHING UNIT
14 | Sending Finishing Trims. | 1 | 2 | MERCHANT & TRIMS SECTION
15 | Finishing (IN HOUSE & OUT SIDE) | 4 |  | FINISHING UNIT
16 | Goods Ready for inward at warehouse. | 1 |  | FINISHING UNIT & WARE HOUSE